## Product Backlog
Product Backlog | [9 empty] | Legenda
ID | Task | Story | Priority | Story Point | Estimated Time | Owner | Sprint | Status | Accetable Criteria
40 | Database connection | Y | H | 100 | 1hr | Giovanmaria | 1 | Done | Create and connect to world database | N | NO
1 | List Country in the World - largest to smallest. | N | H | 100 | [5 empty] | Y | YES
2 | List Country in the continent - largest to smallest. | N | H | 100
3 | List Country in the Region - largest to smallest. | N | H | 100 | [5 empty] | H | High
4 | List Top N populated country in the world. (N) defined by user. | N | H | 100 | [5 empty] | M | Medium
5 | List Top N populated country in the continent. (N) defined by user. | N | H | 100 | [5 empty] | L | Low
6 | List Top N populated country in the region. (N) defined by user. | N | H | 100
7 | List all the cities in the world organised by largest population to smallest. | N | H | 100
8 | List all the cities in the continet organised by largest population to smallest. | N | H | 100
9 | List all the cities in the region organised by largest population to smallest. | N | H | 100
10 | List all the cities in the country organised by largest population to smallest. | N | H | 100
11 | List all the cities in the district organised by largest population to smallest. | N | H | 100
12 | List Top N populated cities in the world. (N) defined by user. | N | H | 100
13 | List Top N populated cities in the continet. (N) defined by user. | N | H | 100
14 | List Top N populated cities in the region. (N) defined by user. | N | H | 100
15 | List Top N populated cities in the country. (N) defined by user. | N | H | 100
16 | List Top N populated cities in the district. (N) defined by user. | N | H | 100
17 | List all capital cities in the world - largest to smallest. | N | H | 100
18 | List all capital cities in a continent - largest to smallest. | N | H | 100
19 | List all capital cities in a district - largest to smallest. | N | H | 100
20 | List Top N populated capital cities in the world. (N) defined by user. | N | H | 100
21 | List Top N populated capital cities in a continet. (N) defined by user. | N | H | 100
22 | List Top N populated capital cities in a region. (N) defined by user. | N | H | 100
23 | List the population of people, people living in cities, and people not living in cities in each continent. | N | H | 100
24 | List the population of people, people living in cities, and people not living in cities in each region. | N | H | 100
25 | List the population of people, people living in cities, and people not living in cities in each country. | N | H | 100
26 | Access to world population. | N | H | 100
27 | Access to continets population. | N | H | 100
28 | Access to regions population. | N | H | 100
29 | Access to countries population. | N | H | 100
30 | Access to discricts population. | N | H | 100
31 | Access to cities population. | N | H | 100
32 | Number of people and world percentage of Chinese, English, Hindi, Spanish and Arabic language user. Greater to smallest. | N | H | 100
33 | Country report Columns : Code - Name - Continet - Region - Population - Capital. | N | H | 100
34 | City report Columns: Name - Country - District - Population. | N | H | 100
35 | Capital City report Columns: Name - Country - Population. | N | H | 100
36 | Population Report provided with the name of Continent - Region - Country. | N | H | 100
37 | Population Report provided with the total population of Continent - Region - Country. | N | H | 100
38 | Population Report provided with the total population of the continent/region/country living in cities (including a %). | N | H | 100
39 | Population Report provided with the total population of the continent/region/country not living in cities (including a %). | N | H | 100

## Meeting
Meeting
Date | Info | Members