## Product Backlog
Product Backlog
ID | Task | Story | Priority | Story Point | Estimated Time | Owner | Sprint | Status | Accetable Criteria
40 | Database connection | N | H | 100 | 1hr | Giovanmaria | 1 | Done | Create and connect to world database
1 | List Country in the World - largest to smallest. | N | H | 100 | 2hr | Matthew | 2 | Done | Show the list
2 | List Country in the continent - largest to smallest. | N | H | 100 | 2hr | Matthew | 2 | Done | Show the list
3 | List Country in the Region - largest to smallest. | N | H | 100 | 2hr | Matthew | 2 | Done | Show the list
4 | List Top N populated country in the world. (N) defined by user. | N | H | 100 | 2hr | Matthew | 2 | Done | Show the list with Limit
5 | List Top N populated country in the continent. (N) defined by user. | N | H | 100 | 2hr | Matthew | 2 | Done | Show the list with Limit
6 | List Top N populated country in the region. (N) defined by user. | N | H | 100 | 2hr | Matthew | 2 | Done | Show the list with Limit
7 | List all the cities in the world organised by largest population to smallest. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list
8 | List all the cities in the continet organised by largest population to smallest. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list
9 | List all the cities in the region organised by largest population to smallest. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list
10 | List all the cities in the country organised by largest population to smallest. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list
11 | List all the cities in the district organised by largest population to smallest. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list
12 | List Top N populated cities in the world. (N) defined by user. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list with Limit
13 | List Top N populated cities in the continet. (N) defined by user. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list with Limit
14 | List Top N populated cities in the region. (N) defined by user. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list with Limit
15 | List Top N populated cities in the country. (N) defined by user. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list with Limit
16 | List Top N populated cities in the district. (N) defined by user. | N | H | 100 | 2hr | Giovanmaria | 2 | Done | Show the list with Limit
26 | Access to world population. | N | H | 100 | 2hr | Giovanmaria | 3 | Done | Show world population
27 | Access to continets population. | N | H | 100 | 2hr | Giovanmaria | 3 | Done | Show continent population
28 | Access to regions population. | N | H | 100 | 2hr | Giovanmaria | 3 | Done | Show region population
29 | Access to countries population. | N | H | 100 | 2hr | Giovanmaria | 3 | Done | Show country population
30 | Access to discricts population. | N | H | 100 | 2hr | Giovanmaria | 3 | Done | Show district population
31 | Access to cities population. | N | H | 100 | 2hr | Giovanmaria | 3 | Done | Show city population
32 | Number of people and world percentage of Chinese, English, Hindi, Spanish and Arabic language user. Greater to smallest. | N | H | 100 | 2hr | Giovanmaria | 3 | Done | Language speakers and percentage
17 | List all capital cities in the world - largest to smallest. | N | H | 100 | 2hr | Kaitlin | 3 | Done | Show the list
18 | List all capital cities in a continent - largest to smallest. | N | H | 100 | 2hr | Kaitlin | 3 | Done | Show the list
19 | List all capital cities in a district - largest to smallest. | N | H | 100 | 2hr | Kaitlin | 3 | Done | Show the list
20 | List Top N populated capital cities in the world. (N) defined by user. | N | H | 100 | 2hr | Kaitlin | 3 | Done | Show the list with Limit
21 | List Top N populated capital cities in a continet. (N) defined by user. | N | H | 100 | 2hr | Kaitlin | 3 | Done | Show the list with Limit
22 | List Top N populated capital cities in a region. (N) defined by user. | N | H | 100 | 2hr | Kaitlin | 3 | Done | Show the list with Limit
23 | List the population of people, people living in cities, and people not living in cities in each continent. | N | H | 100 | 2hr | Marcin | 3 |  | Show the list
24 | List the population of people, people living in cities, and people not living in cities in each region. | N | H | 100 | 2hr | Marcin | 3 |  | Show the list
25 | List the population of people, people living in cities, and people not living in cities in each country. | N | H | 100 | 2hr | Marcin | 3 |  | Show the list

## Readme Req.
ID | Task | Met | Screen
1 | List Country in the World - largest to smallest. | Yes | ![](Screen/Req1&4.png)
2 | List Country in the continent - largest to smallest. | Yes | ![](Screen/Req2&5.png)
3 | List Country in the Region - largest to smallest. | Yes | ![](Screen/Req3&6.png)
4 | List Top N populated country in the world. (N) defined by user. | Yes | ![](Screen/Req1&4.png)
5 | List Top N populated country in the continent. (N) defined by user. | Yes | ![](Screen/Req2&5.png)
6 | List Top N populated country in the region. (N) defined by user. | Yes | ![](Screen/Req3&6.png)
7 | List all the cities in the world organised by largest population to smallest. | Yes | ![](Screen/Req7&12.png)
8 | List all the cities in the continet organised by largest population to smallest. | Yes | ![](Screen/Req8&13.png)
9 | List all the cities in the region organised by largest population to smallest. | Yes | ![](Screen/Req9&14.png)
10 | List all the cities in the country organised by largest population to smallest. | Yes | ![](Screen/Req10&15.png)
11 | List all the cities in the district organised by largest population to smallest. | Yes | ![](Screen/Req11&16.png)
12 | List Top N populated cities in the world. (N) defined by user. | Yes | ![](Screen/Req7&12.png)
13 | List Top N populated cities in the continet. (N) defined by user. | Yes | ![](Screen/Req8&13.png)
14 | List Top N populated cities in the region. (N) defined by user. | Yes | ![](Screen/Req9&14.png)
15 | List Top N populated cities in the country. (N) defined by user. | Yes | ![](Screen/Req10&15.png)
16 | List Top N populated cities in the district. (N) defined by user. | Yes | ![](Screen/Req11&16.png)
26 | Access to world population. | Yes | ![](Screen/Req26.png)
27 | Access to continets population. | Yes | ![](Screen/Req27.png)
28 | Access to regions population. | Yes | ![](Screen/Req28.png)
29 | Access to countries population. | Yes | ![](Screen/Req29.png)
30 | Access to discricts population. | Yes | ![](Screen/Req30.png)
31 | Access to cities population. | Yes | ![](Screen/Req31.png)
32 | Number of people and world percentage of Chinese, English, Hindi, Spanish and Arabic language user. Greater to smallest. | Yes | ![](Screen/Language.png)
17 | List all capital cities in the world - largest to smallest. | Yes | ![](Screen/Req17&20.png)
18 | List all capital cities in a continent - largest to smallest. | Yes | ![](Screen/Req18&21.png)
19 | List all capital cities in a district - largest to smallest. | Yes | ![](Screen/Req19&22.png)
20 | List Top N populated capital cities in the world. (N) defined by user. | Yes | ![](Screen/Req17&20.png)
21 | List Top N populated capital cities in a continet. (N) defined by user. | Yes | ![](Screen/Req18&21.png)
22 | List Top N populated capital cities in a region. (N) defined by user. | Yes | ![](Screen/Req19&22.png)
23 | List the population of people, people living in cities, and people not living in cities in each continent. | No | ![](Screen/Req23.png)
24 | List the population of people, people living in cities, and people not living in cities in each region. | No | ![](Screen/Req24.png)
25 | List the population of people, people living in cities, and people not living in cities in each country. | No | ![](Screen/Req25.png)